Pilot Plan & Feedback Toolkit

Pathway Orientation: for piloting the workbook in real classrooms before CDC submission

| Document title | Pilot Plan & Feedback Toolkit: Pathway Orientation |
| --- | --- |
| Purpose | Plan and record a real-classroom pilot, and produce the evidence needed for the CDC submission package |
| Companion documents | Pathway Orientation Workbook (PDF); docs/facilitators-guide.docx; docs/syllabus-mapping.docx |
| Status | TOOLKIT ONLY: no pilot has been run yet. This document has not been used in a real school. |
| Version | 0.1 |
| Date | 16 September 2026 |

# 1. Why Pilot This First

Every other document in this submission package was written and designed without yet being tested on a real class. A pilot is what turns “we designed this carefully” into “we tried this with real Form 3/4 learners and here is what happened”, the kind of evidence a curriculum body will expect to see, and the only reliable way to catch problems that only show up with real learners: timing that runs long, wording that confuses, or a sensitive situation the facilitator's guide didn't anticipate.

No pilot has been run yet This toolkit has not been used in a real classroom. It exists so that when a pilot is run, it produces useful, honest evidence rather than an unstructured impression. Do not fill in Section 8 (the Pilot Summary Report) with placeholder or anticipated answers. Leave it blank until an actual pilot has taken place.

# 2. Before You Begin: Permissions and Ethics

- Get written authorisation from the school's Head Teacher before running any session; this is a pilot of unapproved material, not yet a CDC-endorsed reader.

- Notify parents/guardians in advance, in simple terms: a career-guidance self-reflection activity will run during Guidance and Counselling / Civic Education / co-curricular time; it is not a graded test.

- Tell learners plainly that this is a trial version and their honest feedback, including criticism, is wanted and will be used to improve it.

- Follow the facilitator's guide's own ground rules throughout (Section 2 of that document): participation in the activity can be required as normal classwork, but sharing a personal result out loud is always voluntary.

- Do not record any learner's actual Dominant/Secondary/Shadow result as pilot data. Collect only the anonymous, aggregate feedback described in Sections 6–7 below.

# 3. Suggested Pilot Scope

- Two to three schools if possible, chosen to vary rather than to flatter the workbook: at least one under-resourced setting, to genuinely test Section 9 of the facilitator's guide (adaptations for schools without enough printed copies or a photocopier).

- At least two classes; roughly 40–100 learners in total is enough to surface real patterns without needing a large-scale trial.

- One facilitator per class, each having read the facilitator's guide in full beforehand (its own Section 4, Preparation Checklist).

# 4. Suggested Timeline

Adjust freely to the school calendar and to how quickly Sessions 1–3 can actually be scheduled; the exact weeks below are illustrative, not a requirement.

| When | What happens |
| --- | --- |
| Week 1 | Get school authorisation; notify parents/guardians; facilitator reads the full facilitator's guide |
| Week 2 | Run Session 1 (Introduction & Self-Assessment) and Session 2 (Scoring & Reading Your Result) |
| Week 3 | Run Session 3 (World of Work, Decisions, Pathways & Working Together); collect student and facilitator feedback immediately after |
| Week 4 | Compile findings into the Pilot Summary Report (Section 8); decide what, if anything, changes before submission |

# 5. Facilitator Observation Log

Complete one row per session, during or immediately after running it; memory of exact timing and confusing moments fades fast.

| Session | Planned time | Actual time | What worked / what needed rephrasing | Sensitive situations (guide Section 10)? |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |

# 6. Student Feedback Form (anonymous)

No name field. Hand out after Session 3. Read each statement aloud if literacy varies, and remind learners this is about the workbook, not about them; there are no wrong answers here either.

| Statement | 1 No | 2 | 3 Not sure | 4 | 5 Yes |
| --- | --- | --- | --- | --- | --- |
| The instructions were easy to understand. | ☐ | ☐ | ☐ | ☐ | ☐ |
| The questions made sense to me. | ☐ | ☐ | ☐ | ☐ | ☐ |
| My result felt like it described me, at least partly. | ☐ | ☐ | ☐ | ☐ | ☐ |
| I found out about a subject, institution or career I hadn't thought about before. | ☐ | ☐ | ☐ | ☐ | ☐ |
| I would recommend this activity to a friend in another class. | ☐ | ☐ | ☐ | ☐ | ☐ |

Was anything in this workbook confusing, upsetting, or something you think should change? (write freely below)

# 7. Facilitator Feedback Form

To be completed by the facilitator after all three sessions, in their own words.

1. How long did each session actually take, compared with the guide's estimate?

2. Which parts of the facilitator's script needed rephrasing or extra explanation?

3. Did any situations from Section 10 (sensitive situations and FAQs) come up? How did you handle them, and did the guide's suggested response work?

4. Did the Working Together activity (Section 8.3) work as written? Did groups need more or less than 5–8 minutes?

5. Would you recommend this workbook for full rollout in Form 3/4 Guidance and Counselling? Why or why not?

6. Any other comments, corrections, or suggestions?

# 8. Pilot Summary Report

Fill this in only after the pilot has actually taken place. This is the page most worth attaching to the CDC submission package: it is the evidence that Sections 1–7 above exist to produce.

| School(s) involved |  |
| --- | --- |
| Dates piloted |  |
| Number of learners |  |
| Number of facilitators |  |
| Key findings: timing |  |
| Key findings: comprehension issues found and fixed |  |
| Key findings: sensitive situations encountered and how handled |  |
| Overall learner reception |  |
| Overall facilitator reception |  |
| Changes made to the workbook or facilitator's guide as a result |  |

## Sign-off

| Name & position | Signature | Date |
| --- | --- | --- |